## Review Summary
Revised cost review
Municipal Building, The Moor, Falmouth ¦ October 2024 Revision A compared with current review position ¦ GBP, VAT excluded
ORIGINAL PRINTED |  | CURRENT REVIEW |  | MOVEMENT |  | PENDING OPTION (DIRECT)
1971278 |  | 2039472 |  | 68194 |  | 18000
Review position
Item | Original / source | Earlier review | Current review | Movement | Position | Limit treatment | Source
Heating and ASHP | 432000 | 472000 | 458000 | 26000 | Included | Replaces source package within M&E | REV-01
Ventilation | 55000 | - | 55000 | 0 | Included | Unchanged memorandum sum | REV-01
All other elemental works | 810975 | - | 810975 | 0 | Included | Unchanged by default; editable | REV-01
Design-development risk | 10% | - | 12% | 2% | Included | % of base cost | REV-02
Asbestos removal | Excluded | - | 18000 | - | Pending | Outside current limit unless Approved | REV-03
Decision view
Current review cost limit | 2039472 |  | Original full-precision recalculation | 1971277.8525 |  | Price date | 4Q24; inflation to 1Q25
Gross impact if all pending options approved | 22397.76 |  | Current full-precision calculation | 2039471.588 |  | VAT | Excluded
Indicative cost limit including pending options | 2061869 |  | Reconciliation check | 0 |  | Estimate status | Guide of probable current cost
Use and limitations
• Edit yellow cells on Review Inputs and Cost Breakdown during the meeting; linked totals and reconciliation update automatically.
• The current limit includes the £458,000 heating/ASHP package and 12% design-development risk. The £18,000 asbestos option is Pending and excluded.
• Provisional sums are memorandum detail already included within elemental costs. The £3,000 M&E balance is held without assigning it to an unsupported category.
• The estimate remains subject to all Revision A notes, qualifications and exclusions. Source values are traceable on Source References.

## Cost Breakdown
Elemental cost breakdown
Original printed elemental analysis alongside the current review position. Current M&E is linked to package inputs.
RTP scope of works
Ref | Element | Original % | Original amount | Current amount | Current % | Movement | Review position | Source | Review note
EL-01 | Grade 2 Listing | 0% | - | - | 0% | - | Unpriced | SRC-04 | Source dash retained.
EL-02 | Pitched Roof | 29.29% | 418900 | 418900 | 28.77% | 0 | Included - unchanged | SRC-04 | Current defaults to source amount.
EL-03 | Central Lantern Feature | 0.67% | 9600 | 9600 | 0.6592% | 0 | Included - unchanged | SRC-04 | Current defaults to source amount.
EL-04 | Rear Roof (refer to Pitched Roof for costs) | 0.03% | 400 | 400 | 0.02747% | 0 | Included - unchanged | SRC-04 | Source cross-reference retained.
EL-05 | Valley and Parapet Gutters | 1.17% | 16700 | 16700 | 1.147% | 0 | Included - unchanged | SRC-04 | Current defaults to source amount.
EL-06 | Parapet Walls | 0.96% | 13800 | 13800 | 0.9477% | 0 | Included - unchanged | SRC-04 | Current defaults to source amount.
EL-07 | Rainwater Goods | 3.35% | 47950 | 47950 | 3.293% | 0 | Included - unchanged | SRC-04 | Current defaults to source amount.
EL-08 | Masonry | 7.74% | 110725 | 110725 | 7.604% | 0 | Included - unchanged | SRC-04 | Current defaults to source amount.
EL-09 | Rendered Masonry | 0.5% | 7200 | 7200 | 0.4944% | 0 | Included - unchanged | SRC-04 | Current defaults to source amount.
EL-10 | Windows | 6.25% | 89450 | 89450 | 6.143% | 0 | Included - unchanged | SRC-04 | Current defaults to source amount.
EL-11 | Rooflights | 1.13% | 16100 | 16100 | 1.106% | 0 | Included - unchanged | SRC-04 | Spelling normalised; amount unchanged.
EL-12 | Lantern Light and Skylight | 3.28% | 46950 | 46950 | 3.224% | 0 | Included - unchanged | SRC-04 | Current defaults to source amount.
EL-13 | Doors | 1.05% | 15000 | 15000 | 1.03% | 0 | Included - unchanged | SRC-04 | Current defaults to source amount.
EL-14 | Walls | 1.27% | 18200 | 18200 | 1.25% | 0 | Included - unchanged | SRC-04 | Current defaults to source amount.
EL-15 | Mechanical and Electrical Services | 43.3% | 619250 | 645250 | 44.31% | 26000 | Included - revised | SRC-03 / SRC-04 / REV-01 | Source element plus net movement in listed M&E package inputs; residual balance held unchanged.
TOTAL | RTP Scope of Works - Total | 99.99% | 1430225 | 1456225 | 100% | 26000 | Current elemental total | SRC-04 | Original amount is the printed total; current total excludes unapproved options.
| Check: sum of original lines less printed total |  | 0 | [5 empty] | Expected £0.
Note on E7: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E8: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E9: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E10: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E11: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E12: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E13: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E14: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E15: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E16: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E17: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E18: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E19: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E20: Editable current element amount. Source amount remains unchanged in the adjacent column.
Note on E21: Calculated from the M&E package inputs and the unallocated source balance on Review Inputs.

## Review Inputs
Review inputs
Yellow cells are meeting inputs. Current defaults follow the review correspondence dated in the supplied benchmark.
Included M&E package pricing
Ref | Package / memorandum item | Source amount | Earlier review | Current input | Movement | Position | Source | Treatment / qualification
PKG-01 | Electrical power and lighting | 85750 |  | 85750 | 0 | Included | SRC-03 | Memorandum provisional sum within M&E; unchanged in review.
PKG-02 | Water services | 43500 |  | 43500 | 0 | Included | SRC-03 | Memorandum provisional sum within M&E; unchanged in review.
PKG-03 | Heating and air-source heat pump | 432000 | 472000 | 458000 | 26000 | Included | SRC-03 / REV-01 | £472,000 earlier review is superseded. Current package replaces £432,000 source allowance.
PKG-04 | Ventilation | 55000 |  | 55000 | 0 | Included | SRC-03 / REV-01 | Memorandum provisional sum within M&E; correspondence says unchanged.
PKG-SUB | Listed M&E memorandum items subtotal | 616250 |  | 642250 | 26000 | Included | SRC-03 | Subtotal only; these amounts are already included in the elemental M&E total.
PKG-BAL | M&E elemental balance not allocated by source | 3000 |  | 3000 | 0 | Included - held | SRC-03 / SRC-04 | Difference between the £619,250 element and listed M&E memorandum sums. No allocation is assumed.
Options awaiting decision
Ref | Option | Original treatment | Current price | Decision | Included now | Pending amount | Gross limit impact | Source / treatment
OPT-01 | Asbestos removal | Excluded | 18000 | Pending | 0 | 18000 | 22397.76 | SRC-02 / REV-03: outside current limit until approved; price excludes subsequent additions and VAT.
Allowances and additions
Ref | Allowance / addition | Source basis | Current input | Working basis | Source | Qualification
ALL-01 | Main contractor preliminaries | 182800 | 182800 | Fixed amount | SRC-01 | Held unchanged unless edited.
ALL-02 | Main contractor overheads & profit | 10% | 10% | % of works plus preliminaries | SRC-01 | Original basis retained.
ALL-03 | Project consultants fees | Excluded | Excluded | Excluded | SRC-01 / SRC-02 | No amount included.
ALL-04 | Design-development risk | 10% | 12% | % of base cost estimate | SRC-01 / REV-02 | Current rate directed by review correspondence.
ALL-05 | Construction risks | - | - | Source dash | SRC-01 | Unpriced source dash retained; no amount included.
ALL-06 | Employer change risks | - | - | Source dash | SRC-01 | Unpriced source dash retained; no amount included.
ALL-07 | Inflation allowance 4Q24 to 1Q25 | 1% | 1% | % of cost limit before inflation | SRC-01 | Original rate and basis retained.
ALL-08 | VAT | Excluded | Excluded | Excluded | SRC-01 / SRC-02 | Cost limit is VAT excluded.
Note on D18: Editable option price, excluding VAT and subsequent additions.
Note on D25: Editable current allowance input. Formulas update throughout the workbook.
Note on D26: Editable current allowance input. Formulas update throughout the workbook.
Note on D28: Editable current allowance input. Formulas update throughout the workbook.
Note on D31: Editable current allowance input. Formulas update throughout the workbook.
Note on E7: Editable current package price. Enter GBP excluding VAT and subsequent additions.
Note on E8: Editable current package price. Enter GBP excluding VAT and subsequent additions.
Note on E9: Editable current package price. Enter GBP excluding VAT and subsequent additions.
Note on E10: Editable current package price. Enter GBP excluding VAT and subsequent additions.
Note on E18: Choose Pending, Approved or Rejected. Only Approved enters the current cost limit.

## Working Calculation
Working calculation
Full-precision calculations are retained. GBP columns display whole pounds; the option scenario includes all currently pending options.
Estimate summary chain
Cost chain | Basis | Original printed | Original recalculated | Current review | Current + pending options | Movement vs recalculated | Source / treatment
Elemental building works | Cost Breakdown | 1430225 | 1430225 | 1456225 | 1456225 | 26000 | SRC-04
Approved / pending options | Decision-controlled | - | 0 | 0 | 18000 | 0 | REV-03
Building Works | Elemental works + included options | 1430225 | 1430225 | 1456225 | 1474225 | 26000 | SRC-01
Main Contractors Preliminaries | Fixed amount | 182800 | 182800 | 182800 | 182800 | 0 | SRC-01
Cost before overheads & profit | Building works + preliminaries |  | 1613025 | 1639025 | 1657025 | 26000 | Calculated
Main Contractors Overheads & Profit | % of works + preliminaries | 161303 | 161302.5 | 163902.5 | 165702.5 | 2600 | SRC-01
Building Works Estimate | Cost before OHP + OHP | 1774328 | 1774327.5 | 1802927.5 | 1822727.5 | 28600 | SRC-01
Project Consultants Fees | Excluded | Excluded | Excluded | Excluded | Excluded | - | SRC-01 / SRC-02
Base Cost Estimate | Building works estimate | 1774328 | 1774327.5 | 1802927.5 | 1822727.5 | 28600 | SRC-01
Design Development Risks | % of base cost | 177433 | 177432.75 | 216351.3 | 218727.3 | 38918.55 | SRC-01 / REV-02
Construction Risks | Source dash retained | - | - | - | - | - | SRC-01
Employer Change Risks | Source dash retained | - | - | - | - | - | SRC-01
COST LIMIT (Inflation Excluded) | Base + design risk | 1951760 | 1951760.25 | 2019278.8 | 2041454.8 | 67518.55 | SRC-01
Inflation Allowance - 4Q24 to 1Q25 | % of pre-inflation limit | 19518 | 19517.6025 | 20192.788 | 20414.548 | 675.1855 | SRC-01
COST LIMIT (VAT Excluded) | Pre-inflation limit + inflation | 1971278 | 1971277.8525 | 2039471.588 | 2061869.348 | 68193.7355 | SRC-01 / current review
Precision note | The original printed £1,971,278 reconciles to a full-precision recalculation of |  | 1971277.8525 | Printed less recalculated | 0.1475 |  | The source summary rounds displayed components; calculations retain underlying precision.

## Reconciliation
Cost-limit reconciliation
Bridge from the original printed VAT-excluded cost limit to the current review position.
Movement bridge
Step | Movement basis | Movement | Running balance | Source / formula | Comment
Original printed cost limit | October 2024 Revision A | 1971278 | 1971278 | SRC-01 | Printed source fact.
Precision adjustment | Move to full-precision original recalculation | -0.1475 | 1971277.8525 | Working Calculation | Keeps printed-to-recalculated rounding visible.
Elemental package movement | Current elemental total less original | 26000 | 1997277.8525 | Cost Breakdown | Includes heating/ASHP movement and any meeting edits to elemental/package inputs.
Approved options | Decision-controlled direct works | 0 | 1997277.8525 | REV-03 | Pending options remain £0 here.
Preliminaries movement | Current amount less original | 0 | 1997277.8525 | Review Inputs | Fixed amount by default.
OHP movement | Current OHP less recalculated original OHP | 2600 | 1999877.8525 | Working Calculation | Captures rate, base and option effects.
Design risk movement | Current design risk less recalculated original risk | 38918.55 | 2038796.4025 | REV-02 | Current default increases rate from 10% to 12%.
Inflation movement | Current inflation less recalculated original inflation | 675.1855 | 2039471.588 | Working Calculation | Original 1% basis retained by default.
Reconciled current position | Full precision |  | 2039471.588 | 2039471.588 | Running balance should equal current working calculation.
Reconciliation check | Running balance less current working calculation | 0 |  |  | Expected £0.000.
Current review displayed | Rounded to whole pounds |  | 2039472 |  | Workbook presentation basis.
Movement vs original printed | Displayed current less printed source total | 68194 |  |  | Headline movement.

## Source References
Source references
Trace register for source amounts, assumptions, exclusions, review directions and workbook treatment.
ID | Source file | Locator | Category | Source fact / qualification | Workbook treatment
SRC-01 | Falmouth_OCE_October2024_RevA.pdf | PDF p2, Summary | Printed summary | Building works £1,430,225; preliminaries £182,800; OHP 10% / £161,303; Building Works Estimate and Base Cost Estimate £1,774,328; design risk 10% / £177,433; inflation-excluded limit £1,951,760; inflation 1% / £19,518; VAT-excluded limit £1,971,278. Consultants fees excluded; construction and employer change risks shown as dashes. | Printed values retained; separate full-precision recalculation shown.
SRC-02 | Falmouth_OCE_October2024_RevA.pdf | PDF p3, Notes / exclusions | Basis and exclusions | Estimate is a guide of probable current cost and should be studied with the Quantity Surveyor. VAT and professional fees are excluded. Asbestos removal is excluded in item r). | Qualifications retained; asbestos shown as a separate option.
SRC-03 | Falmouth_OCE_October2024_RevA.pdf | PDF p4, Basis of Estimate | M&E source amounts | Indicative ZLC Energy heating/ASHP pricing £432,000 excluding VAT. Memorandum provisional sums: electrical £85,750; water £43,500; heating £432,000; ventilation £55,000. These sums are included within elemental costs. | Package movements adjust the £619,250 M&E element by difference; no unsupported allocation is made.
SRC-04 | Falmouth_OCE_October2024_RevA.pdf | PDF p5, Elemental Analysis | Elemental source | Fifteen printed elemental lines total £1,430,225; Mechanical and Electrical Services is £619,250 (43.30%). | All printed amounts and percentages are retained on Cost Breakdown.
REV-01 | review_correspondence.md | Paragraph 2 | Current package review | Earlier heating/ASHP review price £472,000 superseded by current £458,000. Ventilation and all other works unchanged. | Current heating input £458,000; earlier review shown for context only.
REV-02 | review_correspondence.md | Paragraph 3 | Current risk review | Use 12% design-development risk. Other allowance rates and bases remain as original. | Current design risk input 12%; other defaults retained.
REV-03 | review_correspondence.md | Paragraphs 4-5 | Option / price basis | Asbestos-removal option £18,000 awaits decision and is not approved for current limit. Package/option prices are at original price date and exclude VAT and subsequent fee or allowance additions. | Pending by default; approval control adds price before OHP, risk and inflation.
BRF-01 | review_brief.md | All paragraphs | Workpaper convention | Preserve source facts, dashes, exclusions and memorandum treatment; retain precision and show rounding; keep pending options outside current limit; maintain estimate limitations. | Applied across workbook.
BAS-01 | Falmouth_OCE_October2024_RevA.pdf | PDF p3 | Design information | Based purely on pre-planning drawings from RTP Chartered Building Surveyors; no input from another designer for this project type. | Retained as qualification.
BAS-02 | Falmouth_OCE_October2024_RevA.pdf | PDF p3 | Procurement / phasing | Works assumed in a single phase by a local medium-sized bona-fide contractor proficient in this project type. | Retained as qualification.
BAS-03 | Falmouth_OCE_October2024_RevA.pdf | PDF p3 | Programme | Contract duration assumed not to exceed 45 weeks. | Retained as qualification.
BAS-04 | Falmouth_OCE_October2024_RevA.pdf | PDF p3 | Price basis | Present rates are 4Q24 with inflation allowance to 1Q25. BCIS indices were considered unrepresentative of Cornwall cost increases. | 1% source inflation allowance retained by default.
BAS-05 | Falmouth_OCE_October2024_RevA.pdf | PDF p3 | Provisional sums | Provisional sums are included for several items and listed in the Basis of Estimate. | Shown as memorandum detail; not double counted.
PS-01 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | Provisional sum | Structural appraisal of existing timbers £2,000. | Memorandum only; included in elemental costs.
PS-02 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | Provisional sum | Improve ventilation to opening vents on central lantern £1,000. | Memorandum only; included in elemental costs.
PS-03 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | Provisional sum | General repairs to central lantern £2,000. | Memorandum only; included in elemental costs.
PS-04 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | Provisional sum | Venturi System £10,000. | Memorandum only; included in elemental costs.
PS-05 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | Provisional sum | Bird deterrent measures £25,000. | Memorandum only; included in elemental costs.
PS-06 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | Provisional sum | Repairs to external cills £1,500. | Memorandum only; included in elemental costs.
PS-07 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | Provisional sum | External doors (pair of), 3 nr, £15,000. | Memorandum only; included in elemental costs.
PS-08 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | Provisional sum | External area for heating plant £2,500. | Memorandum only; included in elemental costs.
PS-09 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | Provisional sum | Electrical power and lighting £85,750. | Editable package input; included within M&E element.
PS-10 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | Provisional sum | Water services £43,500. | Editable package input; included within M&E element.
PS-11 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | Provisional sum | Heating £432,000. | Replaced by current £458,000 review input.
PS-12 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | Provisional sum | Ventilation £55,000. | Editable package input; held unchanged by default.
PS-13 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | M&E exclusions | Above-ground drainage, fire safety, security/access control, AWC call alarms, lightning protection and lift works are all excluded. | No amount included.
PS-14 | Falmouth_OCE_October2024_RevA.pdf | PDF p4 | Provisional sum | Scaffolding (enclosed) £160,000. | Memorandum only; included in elemental costs.
EX-a | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion a | Exclusion | Objets d'art and all other art/decorative installations. | No amount included.
EX-b | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion b | Exclusion | Additional fit-out items beyond those listed, including specialist joinery. | No amount included.
EX-c | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion c | Exclusion | CCTV and smart systems. | No amount included.
EX-d | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion d | Exclusion | Specialist lighting installations and fittings beyond standard. | No amount included.
EX-e | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion e | Exclusion | Soil investigation/contamination reports and resulting requirements other than noted. | No amount included.
EX-f | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion f | Exclusion | Decanting of building/rooms and re-installation. | No amount included.
EX-g | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion g | Exclusion | M&E consultant or structural engineer design/specification/reports; no design concluded. | No amount included.
EX-h | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion h | Exclusion | Works/costs from onerous planning conditions, particularly material specification. | No amount included.
EX-i | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion i | Exclusion | Professional fees including Architect, Structural Engineer and Quantity Surveyor. | No amount included.
EX-j | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion j | Exclusion | Ecologist fees. | No amount included.
EX-k | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion k | Exclusion | Cornwall Council planning/building regulations application/inspection fees. | No amount included.
EX-l | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion l | Exclusion | Legal fees. | No amount included.
EX-m | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion m | Exclusion | Interest and other financing costs. | No amount included.
EX-n | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion n | Exclusion | Increased costs from foreign trade tariffs surrounding the UK's withdrawal from the EU. | No amount included.
EX-o | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion o | Exclusion | Increased costs arising from conflicts in Ukraine and the Middle East and impacts on procurement and labour. | No amount included.
EX-p | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion p | Exclusion | Value Added Tax where applicable. | No amount included.
EX-q | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion q | Exclusion | Works in relation to dry rot treatment. | No amount included.
EX-r | Falmouth_OCE_October2024_RevA.pdf | PDF p3, exclusion r | Exclusion | Asbestos removal. | Separate pending option per REV-03.
DOC-01 | Falmouth_OCE_October2024_RevA.pdf | PDF p4, Drawings & Documents | Design documents | RTP drawings P240045-200; P240045-201 Rev A; P240045-202 Rev A; P240045-203 Rev A; Scope of Works for 2024 Renovation and Thermal Upgrade Works. | Source design basis only.
QTE-01 | Falmouth_OCE_October2024_RevA.pdf | PDF p4, Quotations received | Market evidence | References quotations from SSQ Riverstone, Alutec, RM Developments, Storm, Charlestown Joinery and Roofmaker (dates stated in source). | No independent re-pricing performed.