## Summary
Falmouth Municipal Building - Cost estimate Revision A
October 2024 ¦ GBP ¦ Job 3959 ¦ Falmouth Town Council
Working stages retain full precision. Difference = working minus printed; printed source values remain unchanged.
Stage | Printed amount | Printed rate | Working rate | Working amount | Difference | Source | Page | Scope
Building Works | 1430225 |  |  |  |  | Falmouth_OCE_October2024_RevA.pdf | 2
Main Contractors Preliminaries | 182800 |  |  |  |  | Falmouth_OCE_October2024_RevA.pdf | 2
Main Contractors Overheads & Profit | 161303 | 10% | 10% |  |  | Falmouth_OCE_October2024_RevA.pdf | 2
Building Works Estimate | 1774328 |  |  |  |  | Falmouth_OCE_October2024_RevA.pdf | 2
Project Consultants Fees | Excluded |  |  |  |  | Falmouth_OCE_October2024_RevA.pdf | 2 | Excluded
Base Cost Estimate | 1774328 |  |  |  |  | Falmouth_OCE_October2024_RevA.pdf | 2
Design Development Risks | 177433 | 10% | 12% |  |  | Falmouth_OCE_October2024_RevA.pdf | 2
Construction Risks | - |  |  |  |  | Falmouth_OCE_October2024_RevA.pdf | 2 | Source dash; no separate priced allowance
Employer Change Risks | - |  |  |  |  | Falmouth_OCE_October2024_RevA.pdf | 2 | Source dash; no separate priced allowance
COST LIMIT (Inflation Excluded) | 1951760 |  |  |  |  | Falmouth_OCE_October2024_RevA.pdf | 2
Inflation Allowance - 4Q24 to 1Q25 | 19518 | 1% | 1% |  |  | Falmouth_OCE_October2024_RevA.pdf | 2
COST LIMIT (VAT Excluded) | 2039472 |  |  |  |  | Falmouth_OCE_October2024_RevA.pdf | 2
Heating/ASHP replaces the included original package. Design risk is now 12%; other bases and rates are unchanged. Differences retain full precision, including source rounding.
The current heating quotation supersedes the earlier quotation. Asbestos remains an unapproved option outside the current cost limit. No consultant fees or VAT are added.

## Elements
Falmouth Municipal Building - Cost estimate Revision A
October 2024 ¦ GBP ¦ Job 3959 ¦ Falmouth Town Council
Elemental analysis, PDF page 5. Source dashes remain unpriced; working zero is a summation convention.
Item | Printed amount | Printed rate | Working amount | Scope | Source | Page
Grade 2 Listing | - | 0% | 0 | Source dash; not separately priced | Falmouth_OCE_October2024_RevA.pdf | 5
Pitched Roof | 418900 | 29.29% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5
Central Lantern Feature | 9600 | 0.67% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5
Rear Roof (refer to Pitched Roof for costs) | 400 | 0.03% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5
Valley and Parapet Gutters | 16700 | 1.17% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5
Parapet Walls | 13800 | 0.96% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5
Rainwater Goods | 47950 | 3.35% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5
Masonry | 110725 | 7.74% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5
Rendered Masonry | 7200 | 0.5% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5
Windows | 89450 | 6.25% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5
Rooflights | 16100 | 1.13% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5
Lantern Light and Skylight | 46950 | 3.28% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5
Doors | 15000 | 1.05% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5
Walls | 18200 | 1.27% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5
Mechanical and Electrical Services | 619250 | 43.3% |  | Elemental cost | Falmouth_OCE_October2024_RevA.pdf | 5

## Provisional sums
Falmouth Municipal Building - Cost estimate Revision A
October 2024 ¦ GBP ¦ Job 3959 ¦ Falmouth Town Council
Basis of estimate, PDF page 4. These amounts are already within elemental costs.
Item | Printed amount | Scope | Source | Page
Structural appraisal of existing timbers | 2000 | Included within elemental costs; memorandum only | Falmouth_OCE_October2024_RevA.pdf | 4
Improve ventilation to opening vents on central lantern | 1000 | Included within elemental costs; memorandum only | Falmouth_OCE_October2024_RevA.pdf | 4
General repairs to central lantern | 2000 | Included within elemental costs; memorandum only | Falmouth_OCE_October2024_RevA.pdf | 4
Venturi System | 10000 | Included within elemental costs; memorandum only | Falmouth_OCE_October2024_RevA.pdf | 4
Bird deterrent measures | 25000 | Included within elemental costs; memorandum only | Falmouth_OCE_October2024_RevA.pdf | 4
Repairs to external cills | 1500 | Included within elemental costs; memorandum only | Falmouth_OCE_October2024_RevA.pdf | 4
External doors (pair of) - 3nr | 15000 | Included within elemental costs; memorandum only | Falmouth_OCE_October2024_RevA.pdf | 4
External area for heating plant | 2500 | Included within elemental costs; memorandum only | Falmouth_OCE_October2024_RevA.pdf | 4
Electrical Power and Lighting | 85750 | Included within elemental costs; memorandum only | Falmouth_OCE_October2024_RevA.pdf | 4
Water Services | 43500 | Included within elemental costs; memorandum only | Falmouth_OCE_October2024_RevA.pdf | 4
Heating | 432000 | Included within elemental costs; memorandum only | Falmouth_OCE_October2024_RevA.pdf | 4
Ventilation | 55000 | Included within elemental costs; memorandum only | Falmouth_OCE_October2024_RevA.pdf | 4
Scaffolding (enclosed) | 160000 | Included within elemental costs; memorandum only | Falmouth_OCE_October2024_RevA.pdf | 4

## Exclusions
Falmouth Municipal Building - Cost estimate Revision A
October 2024 ¦ GBP ¦ Job 3959 ¦ Falmouth Town Council
Explicit exclusions, PDF pages 3 and 4. No zero-priced offers are implied.
Item | Printed amount | Scope | Source | Page
Objets d'art & all other art/decorative installations | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Additional fit out items including specialist joinery | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
CCTV, smart systems | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Specialist lighting installations and light fittings above standard | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Soil investigation/contamination reports and resulting requirements | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
De-canting of building/rooms and re-install | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
M & E consultants or structural engineer design/specification/reports | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Works/costs with onerous planning conditions particularly material specification | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Professional Fees: Architect, Structural Engineer, Quantity Surveyor | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Ecologist fees | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
CC Planning/Building Regulations Application/Inspection Fees | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Legal fees | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Interest and other financing costs | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Increased foreign trade tariff costs surrounding UK withdrawal from EU | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Increased costs from conflict in Ukraine and Middle East | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Value Added Tax where applicable | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Dry rot treatment | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Asbestos removal | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 3
Above ground drainage | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 4
Fire Safety | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 4
Security/Access Control | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 4
AWC Call Alarms | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 4
Lightning Protection | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 4
Lift Works | Excluded | Excluded | Falmouth_OCE_October2024_RevA.pdf | 4

## Qualifications
Falmouth Municipal Building - Cost estimate Revision A
October 2024 ¦ GBP ¦ Job 3959 ¦ Falmouth Town Council
Notes and qualifications, PDF page 3.
Item | Printed amount | Scope | Source | Page
Guide to probable current cost |  | Estimate is a guide only to probable current cost | Falmouth_OCE_October2024_RevA.pdf | 3
Consultation with the Quantity Surveyor |  | Study in consultation with the Quantity Surveyor | Falmouth_OCE_October2024_RevA.pdf | 3
Pre-planning drawings |  | Based on RTP pre-planning drawings; no input from another designer | Falmouth_OCE_October2024_RevA.pdf | 3
Works as envisaged |  | Works as envisaged in drawings and specifications in Basis of Estimate | Falmouth_OCE_October2024_RevA.pdf | 3
Single phase contractor |  | Single phase; local medium sized proficient contractor | Falmouth_OCE_October2024_RevA.pdf | 3
Contract duration |  | Contract duration not to exceed 45 weeks | Falmouth_OCE_October2024_RevA.pdf | 3
Price basis and inflation period |  | Rates at 4Q24 with inflation to 1Q25; BCIS indices not representative of Cornwall cost increases | Falmouth_OCE_October2024_RevA.pdf | 3

## Review decisions
Falmouth Municipal Building - Cost estimate Revision A
October 2024 ¦ GBP ¦ Job 3959 ¦ Falmouth Town Council
Project-authored review scenario. Prices share the estimate price date and exclude VAT and subsequent fee/allowance additions.
Item | Printed amount | Working amount | Scope | Source
Current heating / ASHP quotation |  | 458000 | Current same-scope replacement of the included original heating allowance; ventilation and all other works unchanged. | review_correspondence.md
Earlier heating / ASHP quotation | 472000 |  | Superseded by the current quotation; not an additional charge. | review_correspondence.md
Asbestos removal option |  | 18000 | Not approved; excluded from current cost limit. Option price is shown separately. | review_correspondence.md