## Cost Breakdown
COST REVIEW WORKBOOK
Municipal Building, The Moor, Falmouth
October 2024 Revision A - Cost Review
Element / Package | Original Estimate | Current Review | Movement | Notes
BUILDING WORKS ESTIMATE
Grade 2 Listing | 0 | 0
Pitched Roof | 418900 | 418900
Rear Roof | 9600 | 9600
Rear Roof (refer to Pitched Roof for costs) | 400 | 400
Valley and Parapet Gutters | 16700 | 16700
Parapet Walls | 13800 | 13800
Rendered Masonry | 47950 | 47950
Rainwater Goods | 110725 | 110725
Rooflights | 7200 | 7200
Central Lantern Feature | 89450 | 89450
Lantern Light and Skylight | 16100 | 16100
Windows | 46950 | 46950
Doors | 15000 | 15000
Walls | 18200 | 18200
Mechanical and Electrical Services | 619250 | 645250 |  | Heating package updated
Building Works Estimate Total | 1430225
MAIN CONTRACTOR ADDITIONS
Main Contractors Preliminaries | 182800 | 182800
Main Contractors Overheads & Profit | 161303 |  |  | 10% of works + prelims
BUILDING WORKS TOTAL | 1774328
Project Consultants Fees | Excluded | Excluded |  | As per original estimate
COST LIMIT (VAT Excluded) | 1774328
RISK ALLOWANCES
Design Development Risks | 177433 |  |  | Orig 10%, Review 12%
Construction Risks | 0 | 0
Employer Change Risks | 0 | 0
COST LIMIT (Inflation Excluded) | 1951760
Inflation Allowance - 4Q24 to 1Q25 | 19518 |  |  | 1.00% of cost limit
BASE COST ESTIMATE / COST LIMIT | 1971278
OPTIONS AWAITING DECISION
Asbestos Removal | - | 18000 | N/A | Not approved for inclusion

## Working Calculation
WORKING CALCULATION
Editable prices and allowance rates
PACKAGE PRICES (excl. VAT, fees, allowances)
Package | Original Price | Review Price | Notes
Heating & ASHP | 432000 | 458000 | Updated package price
Ventilation | 55000 | 55000 | Unchanged
Electrical Power and Lighting | 85750 | 85750 | Unchanged
Water Services | 43500 | 43500 | Unchanged
Other M&E (balance) | 3000 | 3000 | Small items and rounding
Total M&E Services
ALLOWANCE RATES
Allowance Type | Original Rate | Review Rate | Notes
Main Contractor OH&P | 10% | 10% | % of works + prelims
Design Development Risk | 10% | 12% | Updated from 10% to 12%
Inflation Allowance | 1% | 1% | 4Q24 to 1Q25
SUMMARY RECONCILIATION
Description | Original | Review | Movement
Heating & ASHP package change
Impact on Building Works Total | 1430225
After Prelims & OH&P | 1774328
Design Development Risk @ review rate | 177433
Cost Limit (Inflation Excluded) | 1951760
Inflation Allowance (1.00%) | 19518
COST LIMIT | 1971278

## Reconciliation
COST LIMIT RECONCILIATION
Movement from Original Estimate to Current Review Position
Original Cost Limit (October 2024 Rev A) | 1971278
ADJUSTMENTS:
Changes to Package Prices:
Heating & ASHP package |  | Updated supplier price
Ventilation (no change) | 0
Other M&E packages (no change) | 0
Net Package Price Adjustment
Flow-through Effects:
Main Contractor OH&P (10%) |  | 10% of package change
Building Works Total after flow-through
Changes to Allowance Rates:
Design Development Risk rate change |  | 10% to 12% on updated base
Inflation rate (no change) | 0 | Remains 1.00%
Allowance Rate Changes
Inflation on revised cost limit |  | 1% on higher base
TOTAL MOVEMENT
Current Review Cost Limit
VERIFICATION
Reconciled Cost Limit
Direct Calculation (from Working Calculation sheet)
Difference (should be zero or rounding)

## Source References
SOURCE REFERENCES
Traceability of amounts and qualifications
SOURCE DOCUMENTS
Reference | Document | Date
OCE-A | Order of Cost Estimate - Revision A | October 2024
RC | Review Correspondence | Current
ORIGINAL ESTIMATE AMOUNTS (OCE-A)
Item | Amount (£) | Source
Building Works Estimate | 1430225 | OCE-A Page 5, Elemental Total
Main Contractors Preliminaries | 182800 | OCE-A Page 2, Summary
Main Contractors OH&P (10%) | 161303 | OCE-A Page 2, Summary
Building Works Total | 1774328 | OCE-A Page 2, Summary
Design Development Risk (10%) | 177433 | OCE-A Page 2, Summary
Cost Limit (Inflation Excluded) | 1951760 | OCE-A Page 2, Summary
Inflation Allowance (1.00%) | 19518 | OCE-A Page 2, Summary
Base Cost Estimate | 1971278 | OCE-A Page 2, Summary
M&E PACKAGE BREAKDOWN (OCE-A)
Package | Amount (£) | Source
Heating (incl. ASHP) | 432000 | OCE-A Page 4, Provisional Sum / ZLC Energy Ltd
Ventilation | 55000 | OCE-A Page 4, Provisional Sum / PMS March 2024
Electrical Power and Lighting | 85750 | OCE-A Page 4, Provisional Sum / PMS March 2024
Water Services | 43500 | OCE-A Page 4, Provisional Sum / PMS March 2024
Other M&E (balance to element total) | 3000 | OCE-A Page 5, Element total £619,250 less itemised sums
REVIEW ADJUSTMENTS (RC)
Adjustment | New Value | Source / Notes
Heating & ASHP package price | 458000 | RC: Current package price superseding £472,000 earlier review
Design Development Risk rate | 12% | RC: Updated from 10% in original estimate
Asbestos removal option | 18000 | RC: Awaiting decision, not approved for inclusion in cost limit
QUALIFICATIONS & EXCLUSIONS
Item | Status | Source
VAT | Excluded | OCE-A Page 2, Summary; RC confirmation
Professional Fees (Architect, Engineer, QS) | Excluded | OCE-A Page 3, Exclusions
Planning/Building Regs Fees | Excluded | OCE-A Page 3, Exclusions
Price Date | 4Q24 | OCE-A Page 2; RC: all prices use original price date
Inflation Allowance | To 1Q25 | OCE-A Page 2, Summary
Project Duration | Max 45 weeks | OCE-A Page 3, Note c)
Contract Delivery | Single phase, local medium contractor | OCE-A Page 3, Note b)
Asbestos removal | Excluded from cost limit | OCE-A Page 3 item n); RC: option awaiting approval
NOTES
1. All amounts retain full precision in calculations and display rounded to whole pounds.
2. Review correspondence preserves original estimate's allowance rates except Design Development Risk.
3. Package prices exclude VAT and subsequent fee or allowance additions (per RC).
4. Options awaiting decision remain outside the current cost limit when only price changes.
5. This remains an estimate subject to source document qualifications and exclusions.